## Slide 1
PSIA–NRM BOARD · JUNE 17–18, 2026
Our Mountain
A unified plan for the next twelve months
1
WEBSITE
Summer 2026
2
ENGAGEMENT
Summer–Fall 2026
3
PHILANTHROPY
January 2027
Nick Dawson · NRM Board of Directors

## Slide 2
THE BIG IDEA
Three initiatives, one flywheel
These aren't three projects competing for attention. Each one builds the audience and the assets the next one needs.
The Website
THE INFRASTRUCTURE
A modern hub members actually want to use — the home base everything else points to.
Engagement
THE AUDIENCE & TRUST
Real content that earns attention, drives members to the hub, and builds belonging.
Our Mountain
THE FUNDING
A warmed, engaged community is what makes a serious philanthropy campaign possible.
Our Mountain · PSIA-NRM
2

## Slide 3
THE ROADMAP
How it sequences over twelve months
1
SUMMER 2026
Launch the site
Cut over to new psia-nrm.org
Hosting live on Azure (~$40/mo)
Members log in with PSIA SSO
2
SUMMER–FALL 2026
Build engagement
Flagship video series (Katie & Brenna)
Drive members to the hub
Open member-generated content
3
JANUARY 2027
Launch Our Mountain
Soft-launch the campaign
Warmed by a year of engagement
Board & instructors activate the Three Cs
Our Mountain · PSIA-NRM
3

## Slide 4
UPDATE 1 · THE WEBSITE
Built and board-approved
The prototype is live and reviewed. This is a real, working site — not a mockup.
79
real member profiles
12
regional events live
6
seasons of pathway data
1
login, via PSIA SSO
What members finally get
My Pathway
A personal certification dashboard — see your progress and what's next.
Member Directory
Find peers by discipline, resort, and role — connection beyond your home hill.
Events & Community
Clinics, the directory, gallery, and Discord, all in one place.
Our Mountain · PSIA-NRM
4

## Slide 5
UPDATE 1 · THE WEBSITE
Status: clearing the last hurdle
Everything we control is done. The remaining work is hosting and access from National — and we're driving it hard.
On track
Design, build & content — complete
79 members + events imported
PSIA single-sign-on integration mapped
Hosting plan set: National Azure, ~$40/mo
Target launch: week of Aug 3, 2026
What we're waiting on from National
1
Hosting agreement (Sean + Jeff)
2
Azure subscription + access
3
Server + database provisioned
4
OAuth login credentials
Driving it: nudges sent to Sean (cc Herb) and Herb this week; a weekly status check flags any slip. Fallback to independent hosting if access stalls past June 30.
Our Mountain · PSIA-NRM
5

## Slide 6
UPDATE 2 · MEMBER ENGAGEMENT
The site is the destination. Content is the draw.
A simple funnel: create content worth showing up for, point it at the hub, then let members create the next wave themselves.
STEP 1
Flagship content
Two marquee video series with regional stars (next slide). We produce; they star.
STEP 2
Drive members in
Push the content across socials and Discord — every view routes back to the site.
STEP 3
Member-generated
Once engagement is up, members submit their own clips, stories, and photos.
Our Mountain · PSIA-NRM
6

## Slide 7
UPDATE 2 · FLAGSHIP CONTENT
Two series. Two stars. We do the work.
Both asks are deliberately low-lift: Nick handles all filming, editing, and scripting. Katie and Brenna only have to be the talent.
Katie White
PSIA National Team · Yellowstone Club
Strength & cross-training series
Off-season conditioning for instructors serious about progressing — the dryland work that actually moves the needle on skiing.
Brenna Kelleher
Former PSIA National Team · Big Sky
Movement-analysis & coaching series
We gather video of regional instructors; Brenna delivers voice-over critique and coaching — world-class eyes for every hill.
Why them: National-team credibility signals exactly where NRM is headed — and gives instructors at smaller hills access they'd never otherwise get.
Our Mountain · PSIA-NRM
7

## Slide 8
PHASE 3 · PHILANTHROPY
Our Mountain — and why engagement comes first
The campaign vision is ready. What it needs is an engaged community — which is exactly what Phases 1 and 2 build.
Access & Equity
Every kid learns; every ability included.
Instructor Sustainability
Housing, healthcare, paid certification, safety.
Pathways & Innovation
Careers that last — plus the Innovation Lab.
$50M over 10 years
Three phases: Foundation → Scale → Endowment, anchored by the Innovation Lab moonshot.
SOFT LAUNCH
January 2027
Launched into a community that already cares — not a cold ask.
Our Mountain · PSIA-NRM
8

## Slide 9
WHY THIS WORKS
Engagement is fundraising — a year early
Our Mountain asks the board and instructors to surface the Three Cs. Phase 2 manufactures the first one at scale.
C1
Connection
BUILT IN PHASE 2
A 'why I teach' film or a coaching breakdown is the emotional tie the campaign depends on — created now and ready to deploy.
C2
Capacity
SURFACED LATER
An engaged audience is one you can learn from. Engagement data tells us who's leaning in.
C3
Commitment
PHASE 3 ASK
When the ask comes in 2027, it lands with people who already feel part of the story.
Our Mountain · PSIA-NRM
9

## Slide 10
WHAT I'M ASKING THE BOARD
Endorse the plan — and help me clear the path
1
Endorse the unified plan
Back Site → Engagement → Philanthropy as one sequenced effort, not three.
2
Help unstick National
Herb to close the hosting agreement with Jeff so we hit the summer launch window.
3
Green-light the content
Support engaging Katie and Brenna now, so filming happens this off-season.
4
Hold January 2027 as the target
Agree Our Mountain soft-launches once engagement has had a year to build.
The site is nearly here. The content is ready to shoot. The only question is whether we move together — now.